## Sheet1
JYOTHY INSTITUTE OF TECHNOLOGY
PROJECT WORK BREAK DOWN STRUTCTURE
PROJECT TITLE : ADHD MONITORING SYSTEM FOR BEHAVIORAL CHANGE USING IoT
DATE | BHUVAN SURYA PURUSHOTHAMA B N | VARNASHREE S SHARMA
MILESTONE 1 : DISCUSSING ABOUT PROJECT TITLE
2017-09-06 | Spoke to the project guide about the project
2017-09-07 | Went to CCDD for literature survey
2017-09-08 | Literature survey
2017-09-09 | Activity in college about Project
2017-09-10 | SUNDAY
2017-09-11 | Work on project abstract and block diagram
2017-09-12
2017-09-13
2017-09-14 | Look into AIEEE papers and work on the project abstract
2017-09-15
2017-09-16 | Alumni interaction meet
2017-09-17 | SUNDAY
2017-09-18 | INTERNALS
2017-09-19
2017-09-20
2017-09-21
2017-09-22 | Work on Raspberry pi
2017-09-23
2017-09-24
2017-09-25 | Meet project guide for furthur information
2017-09-26
2017-09-27 | Study on LORA and LOPAN | Study on MQTT and ZIG-BEE
2017-09-28
2017-09-29 | DASARA HOLIDAYS
2017-09-30
2017-10-01
2017-10-02
2017-10-03 | LEAVE FOR VACATION
2017-10-04
2017-10-05
2017-10-06 | Study on LORA and LOPAN
2017-10-07
2017-10-08
2017-10-09 |  | Study on MQTT and ZIG-BEE
2017-10-10
2017-10-11
2017-10-12 | Meet project guide and divide the project into different modules
2017-10-13 | OPEN SOURCE INDIA
2017-10-14
2017-10-15 | MILESTONE 2 : GETTING HARDWARE READY
2017-10-16
2017-10-17 | Discuss upon the components required
2017-10-18 | DEEPAVALI HOLIDAYS
2017-10-19
2017-10-20
2017-10-21 | Get hardware components required
2017-10-22 | SUNDAY
2017-10-23 | Work on Rpi camera | Work on Rpi
2017-10-24
2017-10-25
2017-10-26
2017-10-27 | Work on RFID module
2017-10-28
2017-10-29 | SUNDAY
2017-10-30 | Code for camera on pi | Learn about OpenCV
2017-10-31
2017-11-01 | KANNADA RAJYOTSAVA
2017-11-02
2017-11-03
2017-11-04 | INTERNALS
2017-11-05
2017-11-06
2017-11-07
2017-11-08
2017-11-09
2017-11-10
2017-11-11 | First project review
2017-11-12 | SUNDAY
2017-11-13 | Work on microphone | Work on OpenCV
2017-11-14
2017-11-15
2017-11-16 | LAB INTERNALS
2017-11-17
2017-11-18 | Finish the hardware module of desk | Code the whole software required for hardware
2017-11-19
2017-11-20
2017-11-21
2017-11-22
2017-11-23 | INTERNALS
2017-11-24
2017-11-25
2017-11-26 | Start with the belt module | Start with the software of belt module
2017-11-27
2017-11-28
2017-11-29 | EXTERNAL EXAMINATION
2017-11-30
2017-12-01
2017-12-02
2017-12-03
2017-12-04
2017-12-05
2017-12-06
2017-12-07
2017-12-08
2017-12-09
2017-12-10
2017-12-11
2017-12-12
2017-12-13
2017-12-14
2017-12-15
2017-12-16
2017-12-17
2017-12-18
2017-12-19
2017-12-20
2017-12-21
2017-12-22
2017-12-23
2017-12-24
2017-12-25
2017-12-26
2017-12-27
2017-12-28
2017-12-29
2017-12-30
2017-12-31
2018-01-01
2018-01-02
2018-01-03
2018-01-04
2018-01-05
2018-01-06
2018-01-07
2018-01-08
2018-01-09
2018-01-10
2018-01-11
2018-01-12
2018-01-13
2018-01-14
2018-01-15
2018-01-16
2018-01-17
2018-01-18
2018-01-19
2018-01-20
2018-01-21
2018-01-22
2018-01-23
2018-01-24
2018-01-25
2018-01-26
2018-01-27
2018-01-28
2018-01-29
2018-01-30
2018-01-31
2018-02-01
2018-02-02
2018-02-03
2018-02-04
2018-02-05
2018-02-06
2018-02-07
2018-02-08
2018-02-09
2018-02-10
2018-02-11
2018-02-12
2018-02-13
2018-02-14
2018-02-15
2018-02-16
2018-02-17
2018-02-18
2018-02-19
2018-02-20
2018-02-21
2018-02-22
2018-02-23
2018-02-24
2018-02-25
2018-02-26
2018-02-27
2018-02-28
2018-03-01
2018-03-02
2018-03-03
2018-03-04
2018-03-05
2018-03-06
2018-03-07
2018-03-08
2018-03-09
2018-03-10
2018-03-11
2018-03-12
2018-03-13
2018-03-14
2018-03-15
2018-03-16
2018-03-17
2018-03-18
2018-03-19
2018-03-20
2018-03-21
2018-03-22
2018-03-23
2018-03-24
2018-03-25
2018-03-26
2018-03-27
2018-03-28
2018-03-29
2018-03-30
2018-03-31
2018-04-01
2018-04-02
2018-04-03
2018-04-04
2018-04-05
2018-04-06
2018-04-07
2018-04-08
2018-04-09
2018-04-10
2018-04-11
2018-04-12
2018-04-13
2018-04-14
2018-04-15
2018-04-16
2018-04-17
2018-04-18
2018-04-19
2018-04-20
2018-04-21
2018-04-22
2018-04-23
2018-04-24
2018-04-25
2018-04-26
2018-04-27
2018-04-28
2018-04-29
2018-04-30
2018-05-01
2018-05-02
2018-05-03
2018-05-04
2018-05-05
2018-05-06
2018-05-07
2018-05-08
2018-05-09
2018-05-10
2018-05-11
2018-05-12
2018-05-13
2018-05-14
2018-05-15
2018-05-16
2018-05-17
2018-05-18
2018-05-19
2018-05-20
2018-05-21
2018-05-22
2018-05-23
2018-05-24
2018-05-25
2018-05-26
2018-05-27
2018-05-28
2018-05-29
2018-05-30
2018-05-31